## CostReport
Set Code | Episode | Budget | To Date | This Week | Labor | Man Days | Materials | Rentals | Construction_week | Construction_todate | Construction_budget | Construction_labor | Construction_materials | Construction_rentals | Construction_mandays | Construction_pctremaining | Paint_week | Paint_todate | Paint_budget | Paint_labor | Paint_materials | Paint_rentals | Paint_mandays | Paint_pctremaining | Greens_week | Greens_todate | Greens_budget | Greens_labor | Greens_materials | Greens_rentals | Greens_mandays | Greens_pctremaining | Metal Fab_week | Metal Fab_todate | Metal Fab_budget | Metal Fab_labor | Metal Fab_materials | Metal Fab_rentals | Metal Fab_mandays | Metal Fab_pctremaining | Sculptors_week | Sculptors_todate | Sculptors_budget | Sculptors_labor | Sculptors_materials | Sculptors_rentals | Sculptors_mandays | Sculptors_pctremaining | Remaining | % Remaining
201 | 200 | 17002.00 | 3310.00 | 3310.00 | 370.00 | 2.00 | 2940.00 |  | 200.00 | 200.00 | 3070.00 | 200.00 |  |  | 1.00 | 93 | 59.36 | 59.36 | 3896.00 |  | 59.36 |  |  | 98 | 170.00 | 170.00 | 3250.50 | 170.00 |  |  | 1.00 | 95 |  |  | 3855.50 |  |  |  |  | 100 | 2880.64 | 2880.64 | 2930.00 |  | 2880.64 |  |  | 2 | 13692.00 | 81
202 | 200 | 14076.75 | 9244.16 | 9244.16 | 2028.00 | 8.00 | 7216.16 |  | 4780.40 | 4780.40 | 3797.25 | 502.00 | 4278.40 |  | 2.00 | -26 |  |  | 1291.50 |  |  |  |  | 100 | 3284.76 | 3284.76 | 2433.00 | 347.00 | 2937.76 |  | 2.00 | -35 | 352.00 | 352.00 | 3576.00 | 352.00 |  |  | 2.00 | 90 | 827.00 | 827.00 | 2979.00 | 827.00 |  |  | 2.00 | 72 | 4832.59 | 34
203 | 200 | 18522.00 | 6181.84 | 6181.84 | 686.00 | 5.00 | 5495.84 |  |  |  | 4348.25 |  |  |  |  | 100 | 210.00 | 210.00 | 4098.50 | 210.00 |  |  | 2.00 | 95 | 1265.28 | 1265.28 | 3191.00 | 404.00 | 861.28 |  | 2.00 | 60 | 4634.56 | 4634.56 | 2587.25 |  | 4634.56 |  |  | -79 | 72.00 | 72.00 | 4297.00 | 72.00 |  |  | 1.00 | 98 | 12340.16 | 67
204 | 200 | 17127.75 | 9958.68 | 9958.68 | 843.00 | 5.00 | 9115.68 |  | 150.00 | 150.00 | 4137.25 | 150.00 |  |  | 1.00 | 96 | 4458.72 | 4458.72 | 4582.50 |  | 4458.72 |  |  | 3 | 253.00 | 253.00 | 1897.00 | 253.00 |  |  | 2.00 | 87 | 4656.96 | 4656.96 | 1762.00 |  | 4656.96 |  |  | -164 | 440.00 | 440.00 | 4749.00 | 440.00 |  |  | 2.00 | 91 | 7169.07 | 42
205 | 200 | 17013.75 | 9879.84 | 9879.84 | 2452.00 | 7.00 | 7427.84 |  | 1380.00 | 1380.00 | 6930.25 | 1380.00 |  |  | 4.00 | 80 | 3933.28 | 3933.28 | 2365.00 | 468.00 | 3465.28 |  | 1.00 | -66 | 3962.56 | 3962.56 | 2242.00 |  | 3962.56 |  |  | -77 | 432.00 | 432.00 | 4600.50 | 432.00 |  |  | 1.00 | 91 | 172.00 | 172.00 | 876.00 | 172.00 |  |  | 1.00 | 80 | 7133.91 | 42
206 | 200 | 18112.25 | 9715.24 | 9715.24 | 781.00 | 3.00 | 8934.24 |  | 4925.76 | 4925.76 | 3732.25 |  | 4925.76 |  |  | -32 |  |  | 1754.50 |  |  |  |  | 100 | 781.00 | 781.00 | 2778.50 | 781.00 |  |  | 3.00 | 72 | 4008.48 | 4008.48 | 5180.00 |  | 4008.48 |  |  | 23 |  |  | 4667.00 |  |  |  |  | 100 | 8397.01 | 46
207 | 200 | 14681.00 | 8723.80 | 8723.80 | 1371.00 | 7.00 | 7352.80 |  | 78.00 | 78.00 | 4396.25 | 78.00 |  |  | 1.00 | 98 |  |  | 2269.50 |  |  |  |  | 100 | 2560.48 | 2560.48 | 1521.00 | 204.00 | 2356.48 |  | 1.00 | -68 | 5190.32 | 5190.32 | 2511.25 | 194.00 | 4996.32 |  | 2.00 | -107 | 895.00 | 895.00 | 3983.00 | 895.00 |  |  | 3.00 | 78 | 5957.20 | 41
208 | 200 | 15252.25 | 5221.68 | 5221.68 | 250.00 | 1.00 | 4971.68 |  | 4260.72 | 4260.72 | 1813.00 | 250.00 | 4010.72 |  | 1.00 | -135 | 960.96 | 960.96 | 3504.00 |  | 960.96 |  |  | 73 |  |  | 3295.50 |  |  |  |  | 100 |  |  | 2726.75 |  |  |  |  | 100 |  |  | 3913.00 |  |  |  |  | 100 | 10030.57 | 66
209 | 200 | 18405.75 | 11562.72 | 11562.72 | 1980.00 | 10.00 | 9582.72 |  | 98.00 | 98.00 | 5710.00 | 98.00 |  |  | 1.00 | 98 | 5092.96 | 5092.96 | 2871.00 | 520.00 | 4572.96 |  | 1.00 | -77 | 5231.76 | 5231.76 | 2145.00 | 222.00 | 5009.76 |  | 1.00 | -144 | 698.00 | 698.00 | 3117.75 | 698.00 |  |  | 4.00 | 78 | 442.00 | 442.00 | 4562.00 | 442.00 |  |  | 3.00 | 90 | 6843.03 | 37

## Estimate
Set Code | Episode | Name | Construction Man Days | Construction Materials | Construction Rentals | Paint Man Days | Paint Materials | Paint Rentals | Greens Man Days | Greens Materials | Greens Rentals | Metal Fab Man Days | Metal Fab Materials | Metal Fab Rentals | Sculptors Man Days | Sculptors Materials | Sculptors Rentals | Construction Labor | Paint Labor | Greens Labor | Metal Fab Labor | Sculptors Labor
101 | 100 | Old Ranch | 9.00 | 849.00 | 806.00 | 3.00 | 667.00 | 966.00 | 2.00 | 310.00 | 950.00 | 3.00 | 460.00 | 918.00 | 3.00 | 17.00 | 836.00 | 4950.00 | 900.00 | 600.00 | 1350.00 | 1200.00
102 | 100 | Pacific Street | 4.00 | 350.00 | 489.00 | 6.00 | 595.00 | 627.00 | 6.00 | 321.00 | 549.00 | 7.00 | 664.00 | 127.00 | 5.00 | 244.00 | 441.00 | 2200.00 | 1800.00 | 1800.00 | 3150.00 | 2000.00
103 | 100 | Dusty Ranch | 5.00 | 69.00 | 242.00 | 7.00 | 482.00 | 325.00 | 6.00 | 270.00 | 562.00 | 2.00 | 654.00 | 911.00 | 1.00 | 552.00 | 538.00 | 2750.00 | 2100.00 | 1800.00 | 900.00 | 400.00
104 | 100 | Dusty Ocean | 7.00 | 979.00 | 304.00 | 6.00 | 588.00 | 136.00 | 2.00 | 400.00 | 725.00 | 1.00 | 723.00 | 659.00 |  | 106.00 | 543.00 | 3850.00 | 1800.00 | 600.00 | 450.00
105 | 100 | East Room | 7.00 | 902.00 | 435.00 | 6.00 | 192.00 | 684.00 |  | 283.00 | 643.00 | 7.00 | 962.00 | 683.00 | 8.00 | 672.00 | 696.00 | 3850.00 | 1800.00 |  | 3150.00 | 3200.00
106 | 100 | Spooky Ranch | 1.00 | 206.00 | 881.00 | 6.00 | 357.00 | 776.00 |  | 618.00 | 396.00 | 6.00 | 442.00 | 286.00 | 6.00 | 952.00 | 335.00 | 550.00 | 1800.00 |  | 2700.00 | 2400.00
107 | 100 | East Room | 9.00 | 318.00 | 736.00 |  | 738.00 | 650.00 | 8.00 | 381.00 | 86.00 | 3.00 | 29.00 | 400.00 | 6.00 | 41.00 | 499.00 | 4950.00 |  | 2400.00 | 1350.00 | 2400.00
108 | 100 | Old House | 7.00 | 804.00 | 963.00 | 6.00 | 298.00 | 931.00 | 1.00 | 935.00 | 862.00 | 8.00 | 771.00 | 52.00 | 9.00 | 690.00 | 341.00 | 3850.00 | 1800.00 | 300.00 | 3600.00 | 3600.00
109 | 100 | Deadly Street | 3.00 | 856.00 | 341.00 | 1.00 | 582.00 | 848.00 |  | 315.00 | 540.00 | 3.00 | 220.00 | 536.00 | 9.00 | 977.00 | 722.00 | 1650.00 | 300.00 |  | 1350.00 | 3600.00
201 | 200 | Deadly Ranch | 4.00 | 364.00 | 341.00 | 8.00 | 509.00 | 807.00 | 9.00 | 341.00 | 7.00 | 6.00 | 925.00 | 28.00 | 5.00 | 416.00 | 364.00 | 2200.00 | 2400.00 | 2700.00 | 2700.00 | 2000.00
202 | 200 | Deadly Stairwell | 5.00 | 540.00 | 301.00 | 1.00 | 680.00 | 289.00 | 4.00 | 442.00 | 701.00 | 4.00 | 968.00 | 673.00 | 4.00 | 360.00 | 899.00 | 2750.00 | 300.00 | 1200.00 | 1800.00 | 1600.00
203 | 200 | Dusty House | 5.00 | 789.00 | 603.00 | 9.00 | 761.00 | 435.00 | 6.00 | 724.00 | 532.00 | 3.00 | 178.00 | 958.00 | 7.00 | 309.00 | 978.00 | 2750.00 | 2700.00 | 1800.00 | 1350.00 | 2800.00
204 | 200 | Old Barn | 5.00 | 335.00 | 846.00 | 9.00 | 980.00 | 700.00 | 2.00 | 338.00 | 914.00 |  | 822.00 | 940.00 | 8.00 | 803.00 | 506.00 | 2750.00 | 2700.00 | 600.00 |  | 3200.00
205 | 200 | East Room | 9.00 | 680.00 | 929.00 | 4.00 | 897.00 | 178.00 | 4.00 | 427.00 | 525.00 | 6.00 | 903.00 | 795.00 | 1.00 | 324.00 | 122.00 | 4950.00 | 1200.00 | 1200.00 | 2700.00 | 400.00
206 | 200 | East House | 5.00 | 407.00 | 369.00 | 3.00 | 604.00 | 183.00 | 5.00 | 969.00 | 197.00 | 8.00 | 850.00 | 460.00 | 9.00 | 380.00 | 417.00 | 2750.00 | 900.00 | 1500.00 | 3600.00 | 3600.00
207 | 200 | Juniper Courtyard | 5.00 | 618.00 | 822.00 | 5.00 | 636.00 | 21.00 |  | 544.00 | 977.00 | 3.00 | 570.00 | 490.00 | 7.00 | 922.00 | 51.00 | 2750.00 | 1500.00 |  | 1350.00 | 2800.00
208 | 200 | Tom's Street |  | 986.00 | 827.00 | 8.00 | 345.00 | 579.00 | 5.00 | 917.00 | 766.00 | 5.00 | 219.00 | 89.00 | 6.00 | 692.00 | 641.00 |  | 2400.00 | 1500.00 | 2250.00 | 2400.00
209 | 200 | Dad's Barn | 8.00 | 141.00 | 839.00 | 6.00 | 182.00 | 754.00 | 4.00 | 146.00 | 709.00 | 5.00 | 657.00 | 42.00 | 7.00 | 823.00 | 729.00 | 4400.00 | 1800.00 | 1200.00 | 2250.00 | 2800.00
301 | 300 | Juniper Street | 9.00 | 685.00 | 974.00 | 5.00 | 315.00 | 191.00 | 9.00 | 509.00 | 835.00 | 3.00 | 5.00 | 373.00 | 5.00 | 198.00 | 7.00 | 4950.00 | 1500.00 | 2700.00 | 1350.00 | 2000.00
302 | 300 | Pacific Ridge | 9.00 | 265.00 | 972.00 | 1.00 | 829.00 | 589.00 | 6.00 | 904.00 | 679.00 | 5.00 | 93.00 | 477.00 | 1.00 | 697.00 | 648.00 | 4950.00 | 300.00 | 1800.00 | 2250.00 | 400.00
303 | 300 | Juniper Room | 4.00 | 282.00 | 344.00 | 6.00 | 804.00 | 566.00 |  | 976.00 | 407.00 | 6.00 | 94.00 | 212.00 | 5.00 | 756.00 | 45.00 | 2200.00 | 1800.00 |  | 2700.00 | 2000.00
304 | 300 | Deadly Courtyard | 2.00 | 531.00 | 376.00 | 2.00 | 144.00 | 366.00 | 6.00 | 830.00 | 913.00 | 1.00 | 288.00 | 557.00 | 4.00 | 399.00 | 749.00 | 1100.00 | 600.00 | 1800.00 | 450.00 | 1600.00
305 | 300 | East Ranch | 1.00 | 150.00 | 524.00 |  | 754.00 | 196.00 | 6.00 | 601.00 | 788.00 | 2.00 | 483.00 | 743.00 | 8.00 | 171.00 | 619.00 | 550.00 |  | 1800.00 | 900.00 | 3200.00
306 | 300 | Juniper Room | 4.00 | 251.00 | 779.00 | 3.00 | 835.00 | 639.00 | 8.00 | 590.00 | 312.00 | 6.00 | 797.00 | 393.00 | 4.00 | 746.00 | 418.00 | 2200.00 | 900.00 | 2400.00 | 2700.00 | 1600.00
307 | 300 | Tom's Barn | 6.00 | 532.00 | 153.00 | 8.00 | 498.00 | 104.00 | 3.00 | 914.00 | 568.00 | 7.00 | 871.00 | 707.00 | 8.00 | 988.00 | 472.00 | 3300.00 | 2400.00 | 900.00 | 3150.00 | 3200.00
308 | 300 | Dad's Stairwell | 8.00 | 69.00 | 856.00 | 6.00 | 786.00 | 134.00 | 7.00 | 467.00 | 585.00 | 9.00 | 192.00 | 140.00 | 3.00 | 72.00 | 147.00 | 4400.00 | 1800.00 | 2100.00 | 4050.00 | 1200.00
309 | 300 | East Ridge | 3.00 | 743.00 | 619.00 | 2.00 | 314.00 | 637.00 | 4.00 | 756.00 | 686.00 | 6.00 | 963.00 | 18.00 | 5.00 | 634.00 | 732.00 | 1650.00 | 600.00 | 1200.00 | 2700.00 | 2000.00
401 | 400 | Pacific Room | 9.00 | 470.00 | 565.00 | 6.00 | 91.00 | 578.00 | 3.00 | 659.00 | 556.00 | 5.00 | 460.00 | 548.00 | 3.00 | 928.00 | 257.00 | 4950.00 | 1800.00 | 900.00 | 2250.00 | 1200.00
402 | 400 | Pacific Street |  | 922.00 | 243.00 | 6.00 | 561.00 | 474.00 | 1.00 | 952.00 | 789.00 | 5.00 | 840.00 | 799.00 | 3.00 | 30.00 | 567.00 |  | 1800.00 | 300.00 | 2250.00 | 1200.00
403 | 400 | Juniper Barn | 7.00 | 500.00 | 667.00 | 2.00 | 705.00 | 327.00 | 1.00 | 889.00 | 393.00 | 8.00 | 400.00 | 272.00 | 7.00 | 321.00 | 71.00 | 3850.00 | 600.00 | 300.00 | 3600.00 | 2800.00
404 | 400 | Dusty Courtyard |  | 799.00 | 217.00 | 7.00 | 416.00 | 868.00 | 5.00 | 129.00 | 525.00 | 9.00 | 260.00 | 37.00 | 5.00 | 250.00 | 830.00 |  | 2100.00 | 1500.00 | 4050.00 | 2000.00
405 | 400 | Dusty Ridge | 5.00 | 841.00 | 452.00 | 8.00 | 649.00 | 721.00 | 5.00 | 296.00 | 275.00 | 7.00 | 798.00 | 718.00 | 4.00 | 963.00 | 883.00 | 2750.00 | 2400.00 | 1500.00 | 3150.00 | 1600.00
406 | 400 | Dad's Ranch | 3.00 | 591.00 | 144.00 | 4.00 | 240.00 | 829.00 | 6.00 | 57.00 | 867.00 | 4.00 | 865.00 | 297.00 | 4.00 | 169.00 | 859.00 | 1650.00 | 1200.00 | 1800.00 | 1800.00 | 1600.00
407 | 400 | Juniper Ocean |  | 856.00 | 8.00 |  | 432.00 | 975.00 | 5.00 | 11.00 | 344.00 | 6.00 | 112.00 | 843.00 | 4.00 | 29.00 | 927.00 |  |  | 1500.00 | 2700.00 | 1600.00
408 | 400 | Deadly Ocean | 5.00 | 394.00 | 985.00 | 2.00 | 926.00 | 162.00 | 4.00 | 943.00 | 681.00 | 9.00 | 168.00 | 77.00 | 9.00 | 542.00 | 492.00 | 2750.00 | 600.00 | 1200.00 | 4050.00 | 3600.00
409 | 400 | Spooky Stairwell | 9.00 | 694.00 | 957.00 | 8.00 | 12.00 | 581.00 | 8.00 | 347.00 | 256.00 | 9.00 | 342.00 | 832.00 | 6.00 | 962.00 | 182.00 | 4950.00 | 2400.00 | 2400.00 | 4050.00 | 2400.00
501 | 500 | Dad's House | 7.00 | 610.00 | 106.00 | 4.00 | 696.00 | 447.00 | 6.00 | 740.00 | 328.00 | 7.00 | 607.00 | 901.00 | 9.00 | 812.00 | 234.00 | 3850.00 | 1200.00 | 1800.00 | 3150.00 | 3600.00
502 | 500 | East Stairwell | 4.00 | 236.00 | 248.00 | 6.00 | 168.00 | 238.00 | 1.00 | 65.00 | 434.00 | 5.00 | 957.00 | 499.00 | 7.00 | 550.00 | 600.00 | 2200.00 | 1800.00 | 300.00 | 2250.00 | 2800.00
503 | 500 | Juniper Ocean |  | 385.00 | 307.00 | 5.00 | 245.00 | 392.00 |  | 954.00 | 322.00 |  | 153.00 | 349.00 | 1.00 | 23.00 | 702.00 |  | 1500.00 |  |  | 400.00
504 | 500 | Pacific Room | 7.00 | 918.00 | 928.00 | 1.00 | 33.00 | 736.00 | 9.00 | 532.00 | 795.00 | 5.00 | 238.00 | 995.00 | 9.00 | 298.00 | 408.00 | 3850.00 | 300.00 | 2700.00 | 2250.00 | 3600.00
505 | 500 | Tom's Barn | 8.00 | 338.00 | 88.00 | 4.00 | 898.00 | 309.00 | 9.00 | 794.00 | 251.00 | 2.00 | 572.00 | 901.00 |  | 25.00 | 295.00 | 4400.00 | 1200.00 | 2700.00 | 900.00
506 | 500 | Dad's Ranch | 9.00 | 226.00 | 800.00 | 7.00 | 70.00 | 560.00 | 8.00 | 185.00 | 44.00 |  | 178.00 | 866.00 | 6.00 | 527.00 | 1.00 | 4950.00 | 2100.00 | 2400.00 |  | 2400.00
507 | 500 | Juniper Stairwell | 4.00 | 830.00 | 461.00 | 6.00 | 527.00 | 775.00 | 8.00 | 714.00 | 738.00 | 5.00 | 209.00 | 534.00 | 9.00 | 950.00 | 905.00 | 2200.00 | 1800.00 | 2400.00 | 2250.00 | 3600.00
508 | 500 | East Ocean | 7.00 | 103.00 | 101.00 | 3.00 | 90.00 | 374.00 | 1.00 | 727.00 | 921.00 | 6.00 | 792.00 | 712.00 | 7.00 | 20.00 | 205.00 | 3850.00 | 900.00 | 300.00 | 2700.00 | 2800.00
509 | 500 | Dad's Ranch | 2.00 | 15.00 | 438.00 | 6.00 | 848.00 | 770.00 | 3.00 | 399.00 | 302.00 | 9.00 | 238.00 | 936.00 | 3.00 | 402.00 | 686.00 | 1100.00 | 1800.00 | 900.00 | 4050.00 | 1200.00

## Purchases
Department | PO Num | Supplier | Description | Amount | GST | PST | Week | Total | Set Code | Episode | Date
Paint | 105407 | Pacific Sheetrock | Pacific Supplies | 1207.00 | 5 | 7 | 1 | 1351.84 | 103 | 100 | 12/11/2021
Sculptors | 358814 | Mike's Tools | East Coast Supplies | 4492.00 | 5 | 7 | 1 | 5031.04 | 103 | 100 | 12/11/2021
Greens | 065274 | Windsor Tools | Windsor Metal | 3422.00 | 5 | 7 | 1 | 3832.64 | 104 | 100 | 12/12/2021
Metal Fab | 642716 | Jim's Metal | Windsor Hardware | 3408.00 | 5 | 7 | 1 | 3816.96 | 104 | 100 | 12/13/2021
Metal Fab | 876030 | Jim's Hardware | Jim's Supplies | 2877.00 | 5 | 7 | 1 | 3222.24 | 105 | 100 | 12/14/2021
Greens | 678364 | Mike's Hardware | Windsor Supplies | 3800.00 | 5 | 7 | 1 | 4256.00 | 105 | 100 | 12/12/2021

## Rates
Code | Rate
GP | 37
GH | 25
LGP | 34
PC | 48
LP | 27
P | 34
PL | 50
WH | 52
MF | 43
MFH | 54
SMF | 38
LS | 40
S | 43
MM | 36

## Rentals
Rental Name
Paint Coordinator Kit
Greensperson Kit
Sculptor Kit

## Crew
username | Name | Position | Date Joined | Department | Sun | Sun_set | Mon | Mon_set | Tue | Tue_set | Wed | Wed_set | Thu | Thu_set | Fri | Fri_set | Rentals | Total
jimstern@gmail.com | Jim Stern | CD | 12/16/2021 | Construction | 1 | 102 | 1 | 506 | 7 | 401 | 5 | 401 | 7 | 506 | 4 | 401 |  | 650.00
susancunningham@gmail.com | Susan Cunningham | MFH | 12/13/2021 | Metal Fab | 8 | 104 | 8 | 301 | 7 | 209 | 6 | 101 | 8 | 205 | 1 | 209 |  | 2052.00
edwardmacdonald@hotmail.com | Edward MacDonald | GP | 12/17/2021 | Greens | 11 | 206 | 6 | 209 | 9 | 405 | 10 | 203 | 6 | 401 | 6 | 409 | 120.00 | 1896.00
edwardbrisebois@gmail.com | Edward Brisebois | LCL | 12/16/2021 | Construction | 8 | 304 | 2 | 107 | 6 | 109 | 4 | 309 | 3 | 303 | 5 | 409 |  | 952.00
markmcmichael@hotmail.com | Mark McMichael | GP | 12/13/2021 | Greens | 5 | 204 | 9 | 302 | 5 | 109 | 6 | 202 | 6 | 508 | 6 | 301 |  | 1369.00
mikecunningham@yahoo.ca | Mike Cunningham | MF | 12/14/2021 | Metal Fab | 6 | 101 | 9 | 305 | 10 | 307 | 1 | 507 | 4 | 307 | 2 | 207 |  | 1376.00
bobgranlund@hotmail.com | Bob Granlund | CL | 12/12/2021 | Construction | 6 | 401 | 8 | 403 | 10 | 308 | 3 | 408 | 3 | 502 | 7 | 404 |  | 1739.00
darlenedwyer@gmail.com | Darlene Dwyer | SMF | 12/10/2021 | Metal Fab | 5 | 209 | 4 | 403 | 1 | 304 | 5 | 202 | 7 | 305 | 2 | 209 |  | 912.00
joedwyer@gmail.com | Joe Dwyer | S | 12/16/2021 | Sculptors | 11 | 503 | 9 | 207 | 3 | 107 | 7 | 109 | 3 | 108 | 5 | 409 | 660.00 | 2294.00
bobjenkins@google.ca | Bob Jenkins | CC | 12/10/2021 | Construction | 10 | 108 | 9 | 307 | 10 | 205 | 4 | 305 | 7 | 507 | 5 | 503 | 60.00 | 2310.00
jimwyatt@yahoo.ca | Jim Wyatt | LGP | 12/10/2021 | Greens | 1 | 203 | 2 | 308 | 1 | 402 | 7 | 206 | 4 | 303 | 4 | 206 |  | 646.00
michellehall@gmail.com | Michelle Hall | GH | 12/14/2021 | Greens | 10 | 106 | 5 | 202 | 6 | 108 | 3 | 307 | 4 | 408 | 8 | 309 |  | 900.00
susanlindholm@hotmail.com | Susan Lindholm | CF | 12/10/2021 | Construction | 2 | 109 | 4 | 305 | 2 | 301 | 6 | 107 | 5 | 501 | 4 | 307 | 120.00 | 1040.00
mikecrosby@hotmail.com | Mike Crosby | LS | 12/12/2021 | Sculptors | 1 | 505 | 1 | 107 | 6 | 402 | 10 | 504 | 9 | 402 | 9 | 406 |  | 1440.00
bobwyatt_2@yahoo.ca | Bob Wyatt | CC | 12/11/2021 | Construction | 1 | 506 | 2 | 403 | 10 | 205 | 8 | 409 | 5 | 208 | 4 | 201 |  | 1500.00
susandaniels@yahoo.ca | Susan Daniels | LS | 12/15/2021 | Sculptors | 10 | 207 | 3 | 103 | 9 | 505 | 11 | 303 | 4 | 508 | 1 | 501 |  | 1520.00
patricklindholm@gmail.com | Patrick Lindholm | LS | 12/13/2021 | Sculptors | 8 | 204 | 10 | 403 | 3 | 509 | 7 | 407 | 11 | 202 | 1 | 104 |  | 1600.00
mikebrisebois@yahoo.ca | Mike Brisebois | CC | 12/16/2021 | Construction | 5 | 109 | 3 | 204 | 5 | 501 | 6 | 106 | 6 | 504 | 5 | 205 |  | 1500.00
darlenescott@hotmail.com | Darlene Scott | CF | 12/17/2021 | Construction | 5 | 109 | 5 | 309 | 10 | 502 | 9 | 308 | 11 | 102 | 8 | 403 |  | 1920.00
markpatterson@hotmail.com | Mark Patterson | CC | 12/14/2021 | Construction | 8 | 402 | 7 | 403 | 9 | 504 | 6 | 509 | 6 | 301 | 7 | 409 |  | 2150.00
susanhall@yahoo.ca | Susan Hall | LS | 12/11/2021 | Sculptors | 4 | 403 | 4 | 501 | 9 | 503 | 5 | 402 | 8 | 209 | 7 | 104 |  | 1480.00
edwardjenkins@gmail.com | Edward Jenkins | LGP | 12/10/2021 | Greens | 2 | 204 | 1 | 104 | 3 | 305 | 1 | 401 | 11 | 306 | 6 | 501 |  | 816.00
susancunningham@google.ca | Susan Cunningham | LCL | 12/11/2021 | Construction | 9 | 102 | 4 | 504 | 10 | 409 | 9 | 308 | 3 | 202 | 7 | 401 |  | 1428.00
susangranlund@google.ca | Susan Granlund | S | 12/11/2021 | Sculptors | 4 | 205 | 2 | 209 | 11 | 403 | 4 | 304 | 9 | 202 | 11 | 308 |  | 1763.00
edwardpaul@hotmail.com | Edward Paul | CB | 12/16/2021 | Construction | 4 | 503 | 7 | 102 | 2 | 405 | 6 | 501 | 9 | 303 | 11 | 305 |  | 1365.00
edwardhall@yahoo.ca | Edward Hall | LS | 12/14/2021 | Sculptors | 6 | 402 | 2 | 306 | 3 | 204 | 1 | 307 | 2 | 301 | 7 | 308 |  | 840.00
jimgranlund@yahoo.ca | Jim Granlund | LGP | 12/13/2021 | Greens | 2 | 407 | 11 | 506 | 5 | 403 | 5 | 301 | 2 | 509 | 6 | 207 |  | 1054.00
marko'reilly@yahoo.ca | Mark O'Reilly | MFH | 12/14/2021 | Metal Fab | 2 | 207 | 3 | 202 | 7 | 104 | 5 | 401 | 3 | 108 | 2 | 107 |  | 1188.00
patrickdaniels@google.ca | Patrick Daniels | CF | 12/13/2021 | Construction | 8 | 409 | 9 | 101 | 1 | 403 | 10 | 202 | 11 | 301 | 8 | 309 |  | 1880.00
patrickmacdonald_8@hotmail.com | Patrick MacDonald | LGP | 12/11/2021 | Greens | 5 | 201 | 2 | 409 | 10 | 102 | 4 | 503 | 5 | 304 | 4 | 305 |  | 1020.00
mikegranlund@gmail.com | Mike Granlund | MM | 12/12/2021 | Sculptors | 2 | 308 | 2 | 504 | 6 | 409 | 2 | 203 | 1 | 209 | 3 | 207 |  | 576.00
mikeperkins@yahoo.ca | Mike Perkins | MM | 12/14/2021 | Sculptors | 9 | 303 | 5 | 508 | 9 | 506 | 1 | 106 | 7 | 501 | 10 | 107 |  | 1476.00
joelindholm@yahoo.ca | Joe Lindholm | CD | 12/11/2021 | Construction | 2 | 507 | 7 | 401 | 6 | 503 | 5 | 205 | 11 | 106 | 2 | 503 |  | 858.00
edwardjenkins@google.ca | Edward Jenkins | SC | 12/14/2021 | Construction | 4 | 405 | 7 | 406 | 2 | 209 | 3 | 507 | 3 | 304 | 5 | 507 |  | 1176.00
bobgranlund_8@google.ca | Bob Granlund | CD | 12/10/2021 | Construction | 8 | 309 | 3 | 207 | 11 | 507 | 7 | 405 | 6 | 104 | 6 | 503 |  | 1066.00